3-Month Development Plan

Given your target:

- Development Start: 1 October 2026

- Target Launch: End of December 2026

- Development Duration: ~13 weeks

- Development Phases: 10

- Objective: Full-featured production-ready BuildWyse.in, not merely a prototype

There is one important planning assumption: the 10 phases cannot be purely sequential. Several workstreams—frontend, Supabase schema, AI, integrations, QA, and DevOps—must run in parallel. Otherwise, fitting the complete platform into ~13 weeks is unrealistic.

I would therefore structure the project as 10 controlled development phases with deliberate overlap, with a production freeze before the final launch.

1. Overall 13-Week Timeline

| Phase | Development Period | Duration | Primary Objective |
| --- | --- | --- | --- |
| Phase 1 | 1 Oct – 7 Oct | 1 week | Architecture, repository, environments & foundation |
| Phase 2 | 5 Oct – 14 Oct | 10 days | Authentication, verification & user ecosystem |
| Phase 3 | 10 Oct – 23 Oct | 2 weeks | Client module & AI project discovery |
| Phase 4 | 19 Oct – 30 Oct | 12 days | AI documentation, budget & development preference |
| Phase 5 | 26 Oct – 8 Nov | 2 weeks | Freelancer, teams, enterprise & AI matching |
| Phase 6 | 2 Nov – 22 Nov | 3 weeks | Core project execution & milestone system |
| Phase 7 | 16 Nov – 29 Nov | 2 weeks | AI verification, project health & calendars |
| Phase 8 | 23 Nov – 6 Dec | 2 weeks | CRMS, ASSM & project history |
| Phase 9 | 30 Nov – 13 Dec | 2 weeks | Payments, certification, notifications & admin |
| Phase 10 | 7 Dec – 31 Dec | 3.5 weeks | Full integration, security, QA, deployment & launch |

Note: The overlapping dates are intentional. Multiple engineering teams/workstreams operate simultaneously.

2. Phase 1 — Architecture & Engineering Foundation

1 October – 7 October 2026

| Work Area | Development Work | Deliverable |
| --- | --- | --- |
| Product architecture | Finalize BuildWyse system architecture | Approved architecture |
| Repository | Create GitHub repository | Main codebase |
| Frontend | Initialize Next.js + TypeScript | Working frontend |
| UI | Configure Tailwind + shadcn/ui | Design foundation |
| Backend | Initialize Supabase project | Backend environment |
| Database | Create initial PostgreSQL schema | Initial schema |
| Auth | Configure Supabase Auth | Authentication foundation |
| Storage | Configure Supabase Storage buckets | File infrastructure |
| RLS | Establish security policies | Initial authorization |
| Edge Functions | Create Edge Function structure | Serverless backend |
| AI | Create OpenAI integration layer | Secure AI gateway |
| Environment | Development/staging configuration | Environment separation |
| CI/CD | GitHub Actions | Automated pipeline |
| Testing | Vitest + Playwright foundation | Test infrastructure |
| Monitoring | Sentry integration | Error monitoring |
| Documentation | Technical architecture documentation | Developer reference |

Phase Completion Criteria

| Requirement | Status Target |
| --- | --- |
| Frontend boots | 100% |
| Supabase connected | 100% |
| Database migrations working | 100% |
| Authentication foundation | 100% |
| OpenAI server-side connection | 100% |
| CI/CD | 100% |
| Development environment | 100% |
| Staging environment | 100% |

3. Phase 2 — Authentication, Verification & User Ecosystem

5 October – 14 October 2026

This phase establishes the identity layer for the entire platform.

| Module | Development Work |
| --- | --- |
| Client registration | Client account creation |
| Freelancer registration | Freelancer account creation |
| Organization registration | Enterprise registration |
| Email verification | Supabase Auth |
| Phone verification | OTP integration |
| Identity verification | KYC integration |
| Government ID | Secure document submission |
| Freelancer interview | Interview workflow |
| Freelancer verification | Verification status |
| Profile | Common user profile |
| Freelancer profile | Skills, experience, portfolio |
| Company profile | Company information |
| Team profile | Team information |
| RBAC | Client/freelancer/team/company/admin |
| RLS | Database-level access |
| Admin | Verification management |
| Audit | Verification audit trail |

Deliverable

By the end of this phase, BuildWyse should have a functioning identity ecosystem.

A user should be able to:

- Register.

- Verify email.

- Complete required verification.

- Create their profile.

- Receive an appropriate role.

- Access their dashboard.

- Be restricted from unauthorized data.

4. Phase 3 — Client Module & AI Project Discovery

10 October – 23 October 2026

This is where the actual BuildWyse product experience begins.

| Module | Development Work |
| --- | --- |
| Client dashboard | Dashboard UI |
| Project creation | New project |
| AI project discussion | Conversational interface |
| AI streaming | Real-time AI responses |
| Conversation history | Persistent AI messages |
| Research | AI research capability |
| Requirement questions | Dynamic questions |
| Requirement extraction | Structured JSON |
| Requirement workspace | Review/edit requirements |
| Assumptions | AI assumptions |
| Missing information | Requirement gaps |
| Requirement approval | Client approval |
| Project state | Discovery → requirements |
| Document access | Initial document controls |

AI Development

| AI Component | Work |
| --- | --- |
| System prompt | Requirement AI |
| Conversation memory | Project context |
| Structured output | Requirement schema |
| Research tool | Web research |
| Requirement extraction | JSON schema |
| Requirement validation | Backend validation |
| AI logs | Token/request tracking |
| Prompt versioning | Database/Git |

Phase Deliverable

A client can enter BuildWyse, explain an idea to the AI, answer questions, review structured requirements, and approve the requirement baseline.

5. Phase 4 — Documentation, Budget & Development Preference

19 October – 30 October 2026

This phase transforms the client's requirements into an executable project definition.

| Module | Development Work |
| --- | --- |
| Concept Logic | AI generation |
| PRD | AI generation |
| Technology Stack | AI generation |
| Frontend Specification | AI generation |
| Hardware Specification | AI generation |
| Architecture | AI generation |
| Development Phases | AI generation |
| Document viewer | Frontend |
| Document versioning | Database |
| Document approval | Client |
| Document access | Permission system |
| Budget discussion | AI conversation |
| Market research | AI |
| Individual budget | AI |
| Team budget | AI |
| Enterprise budget | AI |
| Development preference | Client selection |
| Budget approval | Finalization |

Three-Budget Engine

The system must generate:

| Option | Budget |
| --- | --- |
| Individual Freelancer | AI-recommended budget |
| Freelancer Team | AI-recommended budget |
| Enterprise Company | AI-recommended budget |

The client then selects the preferred development model.

Phase Deliverable

The client should finish this phase with:

- Approved requirements.

- Generated project documents.

- Recommended budgets.

- Selected development preference.

- Initial project definition.

6. Phase 5 — Freelancer, Team, Enterprise & AI Matching

26 October – 8 November 2026

This phase builds the marketplace and matching engine.

| Module | Development Work |
| --- | --- |
| Freelancer dashboard | Complete dashboard |
| Freelancer portfolio | Portfolio builder |
| Skills | Skill management |
| Experience | Experience management |
| Certifications | Certification records |
| Individual model | Individual project participation |
| Team creation | Team functionality |
| Team members | Member management |
| Team leader | Leader role |
| Enterprise | Company management |
| Enterprise employees | Employee management |
| Enterprise manager | Manager role |
| Internal roles | Role assignment |
| Project proposal | Candidate proposal |
| Candidate list | Top 10 UI |
| Candidate comparison | Comparison interface |

AI Matching Engine

| Component | Development |
| --- | --- |
| Requirement DNA | Generate structured representation |
| Expertise DNA | Generate freelancer representation |
| Embeddings | Generate vectors |
| pgvector | Store vectors |
| Candidate retrieval | Semantic search |
| Hard filtering | Budget/model/availability |
| Scoring | Deterministic score engine |
| AI explanation | Match explanation |
| Ranking | Top 10 |
| Candidate proposal | Notification |

Client Experience

The client sees the Top 10 candidates with:

- Profile.

- Skills.

- Experience.

- Portfolio.

- Development model.

- Matching score.

- Match explanation.

Freelancer Experience

The freelancer receives the project proposal.

They can:

- Review documentation.

- Accept/reject interest.

- Prepare technical proposal.

- Provide technical perspective.

- Provide project understanding.

7. Phase 6 — Core Project Execution Engine

2 November – 22 November 2026

This is the largest development phase.

The objective is to build the core project execution system.

| Module | Development Work |
| --- | --- |
| Project creation | Final project creation |
| Project workspace | Main project dashboard |
| Project phases | Phase management |
| Milestones | Milestone management |
| Tasks | Task management |
| Deliverables | Deliverable management |
| Deadlines | Deadline management |
| Client dashboard | Project view |
| Freelancer dashboard | Project view |
| Team dashboard | Team project view |
| Enterprise dashboard | Company project view |
| Calendar | Project calendar |
| Submission | Phase submission |
| Evidence | Evidence management |
| GitHub | Repository integration |
| Deployment | Deployment link |
| Photos | Evidence upload |
| Approval | Client approval |
| Rejection | Client remarks |
| Resubmission | Phase resubmission |
| Payment trigger | Milestone approval event |

8. Project Execution Data Model

Each phase should support:

| Data | Purpose |
| --- | --- |
| Phase ID | Identification |
| Phase Name | Phase description |
| Objective | Expected outcome |
| Requirements | Requirements covered |
| Tasks | Work items |
| Deliverables | Expected output |
| Start Date | Schedule |
| Deadline | Schedule |
| Status | Execution state |
| Submission | Freelancer output |
| Evidence | Supporting evidence |
| Verification | AI analysis |
| Client Approval | Acceptance |
| Payment | Financial linkage |

9. Phase 7 — AI Verification, Calendar & Project Health

16 November – 29 November 2026

This phase introduces the platform's project intelligence layer.

AI Verification

| Component | Development |
| --- | --- |
| GitHub connection | Repository retrieval |
| Repository analysis | Code/project analysis |
| Requirement comparison | Requirement vs implementation |
| Deployment verification | Deployment evidence |
| Photo analysis | Vision-based analysis |
| Evidence aggregation | Combined evidence |
| Verification report | AI-generated report |
| Confidence | Verification confidence |
| Findings | Issues/gaps |
| Client report | Client-readable report |

Project Health

| Health Area | Measurement |
| --- | --- |
| Schedule | Deadline performance |
| Milestones | Completion |
| Submission | Delivery consistency |
| Rejections | Rejection frequency |
| Requirements | Scope stability |
| Changes | CR frequency |
| Client satisfaction | Feedback |
| Freelancer satisfaction | Feedback |
| Communication | Interaction |
| Payment | Payment health |
| Overall health | Combined assessment |

Calendar

| Feature | Development |
| --- | --- |
| Client calendar | Project schedule |
| Freelancer calendar | Project schedule |
| Phase deadlines | Calendar events |
| Milestones | Calendar events |
| Meetings | Calendar events |
| Changes | Calendar events |
| Revised deadlines | Calendar updates |
| Reminders | Scheduled notifications |

10. Phase 8 — CRMS + ASSM + Project History

23 November – 6 December 2026

This phase builds the post-baseline project lifecycle.

CRMS

| Feature | Development |
| --- | --- |
| Create CR | Client interface |
| AI discussion | OpenAI |
| Scope comparison | Original vs change |
| Technical impact | AI |
| Architecture impact | AI |
| Database impact | AI |
| API impact | AI |
| Hardware impact | AI |
| Dependencies | AI |
| Effort | AI |
| Timeline | AI |
| Risk | AI |
| Cost | AI |
| Freelancer review | Review workflow |
| Client approval | Approval workflow |
| Timeline revision | Schedule update |
| Budget revision | Financial update |
| CR payment | Payment integration |
| CR execution | Existing phase engine |

ASSM

| Feature | Development |
| --- | --- |
| Project ID lookup | Historical retrieval |
| Original documents | Retrieval |
| Architecture | Retrieval |
| GitHub | Retrieval |
| Deployment | Retrieval |
| Change history | Retrieval |
| Completion records | Retrieval |
| AI service discussion | OpenAI |
| Service documentation | AI |
| Cost estimation | AI |
| Matching | Existing matching |
| Original freelancer priority | Candidate ranking |
| Service execution | Existing execution engine |
| Service payment | Existing payment |
| Service history | Permanent record |

11. Project History Engine

This should be developed during Phase 8 rather than treated as a minor feature.

| Historical Record | Stored |
| --- | --- |
| Original requirements | Yes |
| Approved documents | Yes |
| Budget | Yes |
| Development model | Yes |
| Selected freelancer | Yes |
| Technical proposal | Yes |
| Phases | Yes |
| Milestones | Yes |
| Submissions | Yes |
| AI verification | Yes |
| Approvals | Yes |
| Rejections | Yes |
| Change Requests | Yes |
| Payments | Yes |
| After-sales | Yes |
| Certificate | Yes |

This is what allows ASSM to work effectively.

12. Phase 9 — Payments, Certification, Notifications & Admin

30 November – 13 December 2026

This phase completes the commercial and administrative ecosystem.

Payment System

| Feature | Development |
| --- | --- |
| Payment gateway | Razorpay initially |
| Order creation | Backend |
| Payment page | Client UI |
| Payment confirmation | Webhook |
| Milestone payment | Integration |
| Commission | Backend |
| Freelancer payout | Gateway |
| Refund | Gateway |
| Payment history | Database |
| Invoice | PDF |
| Reconciliation | Backend |
| Payment audit | Database |

Certification

| Feature | Development |
| --- | --- |
| Completion validation | Backend |
| Freelancer certificate | Generation |
| Client certificate | Generation |
| Certificate ID | Database |
| QR verification | QR generation |
| Certificate page | Public verification |
| Storage | Supabase Storage |
| Email | Notification |

Notification System

| Notification | Channel |
| --- | --- |
| Requirement completed | Email + in-app |
| Document generated | Email + in-app |
| Candidate selected | Email + in-app |
| Meeting | Email + in-app |
| Deadline | Email + in-app |
| Submission | Email + in-app |
| Verification | Email + in-app |
| Approval | Email + in-app |
| Rejection | Email + in-app |
| Payment | Email + in-app |
| Change Request | Email + in-app |
| Project health warning | Email + in-app |
| Certificate | Email + in-app |

13. Admin Platform

The admin platform needs to be ready before launch.

| Admin Area | Function |
| --- | --- |
| Dashboard | Platform overview |
| Users | User management |
| Clients | Client management |
| Freelancers | Freelancer management |
| Verification | Identity verification |
| Organizations | Company management |
| Projects | Project oversight |
| Matching | Matching oversight |
| Payments | Financial monitoring |
| CRMS | Change oversight |
| ASSM | Service oversight |
| AI | AI usage monitoring |
| Reports | Platform analytics |
| Disputes | Dispute management |
| Audit | Audit records |
| Certificates | Certificate management |

14. Phase 10 — Full Integration, QA, Security & Launch

7 December – 31 December 2026

This phase is intentionally longer because this is where the platform changes from "working software" to "launchable software."

15. Integration Testing

7–13 December

| Test Area | Work |
| --- | --- |
| Client onboarding | Full flow |
| Freelancer onboarding | Full flow |
| Enterprise onboarding | Full flow |
| AI project discovery | Full flow |
| Documentation | Full flow |
| Budget | Full flow |
| Matching | Full flow |
| Selection | Full flow |
| Project execution | Full flow |
| Verification | Full flow |
| CRMS | Full flow |
| ASSM | Full flow |
| Payment | Full flow |
| Certification | Full flow |

16. Security Testing

10–17 December

| Security Area | Testing |
| --- | --- |
| Authentication | Login/session testing |
| Authorization | RBAC testing |
| RLS | Cross-user data isolation |
| API | Authorization testing |
| Storage | File access testing |
| Payment | Webhook security |
| OpenAI | API key protection |
| GitHub | OAuth/security |
| Input validation | Injection testing |
| XSS | Frontend security |
| CSRF | Request protection |
| Rate limiting | Abuse testing |
| File uploads | Malicious file testing |
| Admin | Privileged access testing |
| Audit | Security event logging |

17. Performance Testing

12–18 December

| Area | Test |
| --- | --- |
| Landing page | Load performance |
| Dashboard | Rendering |
| Project workspace | Large data |
| AI chat | Response handling |
| Matching | Candidate search |
| Database | Query performance |
| Storage | Large file uploads |
| Realtime | Concurrent users |
| APIs | Load testing |
| Payments | Transaction processing |

18. AI Quality Testing

12–20 December

This deserves its own testing period.

| AI Module | Testing |
| --- | --- |
| Requirement AI | Requirement completeness |
| Research AI | Research accuracy |
| Documentation AI | Document quality |
| Budget AI | Recommendation consistency |
| Matching AI | Candidate relevance |
| Proposal AI | Technical understanding |
| Verification AI | False positives/negatives |
| Project Health AI | Correct assessment |
| CRMS AI | Impact analysis |
| ASSM AI | Historical context |

AI should be tested against predefined reference cases rather than only manually chatting with it.

19. UAT — User Acceptance Testing

18–22 December

Prepare controlled users for:

Client Testing

- Registration.

- Verification.

- Project creation.

- AI discussion.

- Documents.

- Budget.

- Freelancer selection.

- Project tracking.

- Approval.

- CRMS.

- ASSM.

- Payments.

- Certificate.

Freelancer Testing

- Registration.

- Verification.

- Portfolio.

- Matching.

- Proposal.

- Project acceptance.

- Calendar.

- Submission.

- Verification.

- CRMS.

- Payment.

- Certificate.

Enterprise Testing

- Company registration.

- Manager.

- Employee accounts.

- Team creation.

- Role assignment.

- Project assignment.

- Submission.

- Verification.

Admin Testing

- Verification.

- User management.

- Project monitoring.

- Payments.

- AI monitoring.

- Audit.

20. Bug Fix & Stabilization Window

20–24 December

At this stage:

No major new features should be introduced.

| Activity | Objective |
| --- | --- |
| P0 bugs | Immediate resolution |
| P1 bugs | Resolution |
| P2 bugs | Resolution where possible |
| UI inconsistencies | Fix |
| API failures | Fix |
| Database issues | Fix |
| RLS issues | Fix |
| Payment issues | Fix |
| AI failures | Fix |
| Performance issues | Fix |

21. Production Deployment

24–27 December

| Activity | Deliverable |
| --- | --- |
| Production Supabase | Production database |
| Production Vercel | Production frontend |
| Domain | BuildWyse.in |
| SSL | HTTPS |
| Environment variables | Production secrets |
| Payment production keys | Live payment |
| OpenAI production key | Production AI |
| GitHub production app | Production integration |
| Email production | Transactional email |
| Monitoring | Sentry |
| Analytics | PostHog |
| Backups | Database backup strategy |
| Logs | Production logging |
| Alerts | Monitoring alerts |

22. Final Launch Readiness

27–29 December

Perform final verification.

| Launch Gate | Requirement |
| --- | --- |
| Authentication | Passed |
| Verification | Passed |
| Client module | Passed |
| Freelancer module | Passed |
| Enterprise module | Passed |
| AI discovery | Passed |
| Documentation | Passed |
| Budget | Passed |
| Matching | Passed |
| Project execution | Passed |
| AI verification | Passed |
| Project health | Passed |
| CRMS | Passed |
| ASSM | Passed |
| Payments | Passed |
| Certification | Passed |
| Notifications | Passed |
| Security | Passed |
| Performance | Passed |
| Monitoring | Passed |

23. Production Launch

30–31 December 2026

The production launch should happen only after the final production smoke test.

Launch Activities

| Activity | Status |
| --- | --- |
| Production deployment | Final |
| DNS | Active |
| SSL | Active |
| Payment gateway | Live |
| OpenAI | Live |
| Email | Live |
| GitHub integration | Live |
| Monitoring | Active |
| Analytics | Active |
| Backup | Active |
| Admin access | Active |
| Launch smoke test | Completed |
| Production sign-off | Completed |

24. Three-Month Development Calendar

| Month | Main Focus |
| --- | --- |
| October | Foundation + Authentication + Client + AI Discovery + Documentation + Budget + Matching |
| November | Freelancer/Enterprise + Matching + Project Execution + Calendar + AI Verification + Project Health + CRMS |
| December | ASSM + Payments + Certification + Admin + Integration + Security + QA + UAT + Deployment + Launch |

25. October Breakdown

| Week | Primary Work |
| --- | --- |
| 1–7 Oct | Architecture, Supabase, Next.js, CI/CD |
| 5–14 Oct | Authentication, verification, profiles |
| 10–17 Oct | Client dashboard |
| 13–23 Oct | AI project discovery |
| 19–30 Oct | Documentation generation |
| 22–30 Oct | Budget + development preference |
| 26–31 Oct | Freelancer/organization foundation |

October Milestone

End of October → Client can define a project, receive AI-generated documentation, receive three development budget options, choose an execution model, and the freelancer ecosystem is operational.

26. November Breakdown

| Week | Primary Work |
| --- | --- |
| 1–8 Nov | AI matching |
| 2–15 Nov | Freelancer/team/enterprise project participation |
| 2–22 Nov | Project execution engine |
| 9–22 Nov | Phases + milestones + submissions |
| 16–29 Nov | AI verification |
| 16–29 Nov | Calendar |
| 16–29 Nov | Project health |
| 23–30 Nov | CRMS |
| 23–30 Nov | ASSM foundation |

November Milestone

End of November → A client can select a verified resource and execute a project through phases, milestones, submissions, AI verification, approvals and project health monitoring. CRMS and ASSM are operational.

27. December Breakdown

| Week | Primary Work |
| --- | --- |
| 1–6 Dec | CRMS + ASSM completion |
| 1–13 Dec | Payments |
| 1–13 Dec | Certification |
| 1–13 Dec | Notifications |
| 1–13 Dec | Admin |
| 7–13 Dec | Full system integration |
| 10–20 Dec | Security/performance/AI testing |
| 18–22 Dec | UAT |
| 20–24 Dec | Bug fixing |
| 24–27 Dec | Production deployment |
| 27–29 Dec | Launch readiness |
| 30–31 Dec | PRODUCTION LAUNCH |

28. Critical Development Dependencies

| Dependency | Must Be Ready Before |
| --- | --- |
| Supabase architecture | All modules |
| Authentication | Client/freelancer modules |
| RLS | All production data |
| User profiles | Matching |
| Requirements | Documentation |
| Documentation | Matching |
| Budget | Development preference |
| Development preference | Matching |
| Freelancer profiles | Matching |
| Matching | Freelancer selection |
| Selection | Project execution |
| Project phases | Milestones |
| Milestones | Payments |
| Evidence | AI verification |
| Original project history | ASSM |
| CRMS | Change execution |
| Payment gateway | Production launch |
| Admin | Production launch |

29. Definition of "Done" for Each Module

A module should not be considered complete merely because its UI exists.

| Module | Definition of Done |
| --- | --- |
| Client | UI + API + DB + RLS + AI + validation + testing |
| Freelancer | Profile + verification + portfolio + DB + permissions |
| Team | Creation + membership + roles + submission |
| Enterprise | Company + employees + manager + roles |
| Matching | Embeddings + scoring + Top 10 + explanation |
| Project | Phases + milestones + tasks + calendar |
| Verification | GitHub + evidence + AI + report |
| Project Health | Data + scoring + dashboard |
| CRMS | AI + impact + cost + approval + execution |
| ASSM | History + AI + matching + execution |
| Payments | Gateway + webhook + ledger + commission |
| Certification | Validation + PDF + verification |
| Notifications | Events + email + realtime |
| Admin | Monitoring + management + audit |
| Security | Auth + RLS + RBAC + testing |
| Deployment | Production + monitoring + backups |

30. Critical Rule for the 3-Month Schedule

The biggest risk is feature creep during November and December.

Therefore, I recommend locking the feature scope at the end of October.

After 1 November, only these should be allowed:

- Required implementation.

- Bug fixes.

- Security improvements.

- Performance improvements.

- Integration requirements.

- Critical UX corrections.

New major features should move to BuildWyse.in V2.

31. V1 Launch Scope

By December 31, V1 should contain the complete core lifecycle:

| Capability | V1 |
| --- | --- |
| Client registration | ✅ |
| Client verification | ✅ |
| Freelancer registration | ✅ |
| Freelancer verification | ✅ |
| Freelancer portfolio | ✅ |
| Teams | ✅ |
| Enterprise companies | ✅ |
| AI requirement discovery | ✅ |
| AI research | ✅ |
| AI documentation | ✅ |
| Budget recommendation | ✅ |
| Three development models | ✅ |
| AI matching | ✅ |
| Requirement/Expertise DNA | ✅ |
| Top 10 candidates | ✅ |
| Technical proposal | ✅ |
| Project phases | ✅ |
| Milestones | ✅ |
| Calendar | ✅ |
| Evidence submission | ✅ |
| GitHub integration | ✅ |
| AI verification | ✅ |
| Client approval | ✅ |
| Project health | ✅ |
| CRMS | ✅ |
| ASSM | ✅ |
| Payment | ✅ |
| Commission | ✅ |
| Certification | ✅ |
| Notifications | ✅ |
| Admin | ✅ |
| Audit history | ✅ |
| Production monitoring | ✅ |

32. Final 3-Month Milestones

| Date | Major Milestone |
| --- | --- |
| 7 Oct | Technical foundation complete |
| 14 Oct | Authentication + verification complete |
| 23 Oct | Client AI discovery complete |
| 30 Oct | Documentation + budget + development preference complete |
| 8 Nov | Freelancer/team/enterprise + matching complete |
| 22 Nov | Core project execution complete |
| 29 Nov | AI verification + health + calendar complete |
| 6 Dec | CRMS + ASSM complete |
| 13 Dec | Payments + certification + admin complete |
| 20 Dec | Full-system testing complete |
| 24 Dec | Feature freeze + stabilization |
| 27 Dec | Production deployment |
| 29 Dec | Final launch readiness |
| 30–31 Dec | 🚀 BUILDWYSE.IN PRODUCTION LAUNCH |

35. The Three-Month Strategy

The development should ultimately follow this priority:

October — BUILD THE FOUNDATION

Build the identity, client discovery, AI requirement engine, documentation, budget system and freelancer ecosystem.

November — BUILD THE EXECUTION ENGINE

Build matching, project execution, milestones, calendars, evidence, AI verification, project health, CRMS and ASSM.

December — MAKE IT PRODUCTION READY

Build payments, certification, notifications and admin, then spend the majority of the final month integrating, testing, securing, stabilizing and deploying the complete platform.

The critical strategic point is that December should not be treated as another feature-development month. By approximately 13 December, the feature set should be functionally complete. The remaining ~2.5 weeks should primarily be dedicated to integration, QA, security, performance, UAT, bug fixing, production deployment and launch preparation.

That is the schedule I would use if the hard requirement is 1 October 2026 → production launch by 31 December 2026 while still aiming for a genuinely full-featured V1 rather than a superficial demo.